## qActiveFY13 ALL
PROJECT_ID | PROJECT_NAME | PROJECT_NAME_SHORT | COUNTRY | REGION | Project Period START_DT | Project Period END_DT | Agreement_Start_Date | Agreement_End_Date | PROPOSAL STATUS | DONOR RECEIVING PROPOSAL | DATE SUBMITTED TO DONOR | STATUS (PMD Pro) | STAFFING_LEVEL | TARGET_Direct_BENEF_LOP | Actual_Direct_Beneficiaries_LOP | SECTOR_PRIMARY | SECTOR_SECONDARY | Project_Implementation | Expr2 | Date_Proposal_Accepted_or_Rejected | Target_Indirect_Beneficiaries_LOP | Target_Direct_Beneficiaries_FY13 | Actual_Direct_Beneficiaries_FY13 | TOTAL LOP BUDGET | FUNDING_SOURCE 1 | Funding Source 1 Amount | FUNDING_SOURCE 2 | Funding Source 2 Amount | FUNDING SOURCE 3 | Funding Source 3 Amount | FUNDING_SOURCE_NOTES | QPR REQUIRED? | PROJ_DESCR_UPDATED | Notes
140 | Resilience in the Americas (RITA) -Nicaragua | IPA- RITA Nicaragua | NICARAGUA | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Field Visits | 200 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 1000 | 200 |  | 100516 | ARC (SIF) | 100516 | [5 empty] | FALSE | TRUE
141 | Resilience in the Americas (RITA) - Costa Rica | IPA- RITA Costa Rica | COSTA RICA | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Field Visits | 400 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 51000 | 400 |  | 110794 | ARC (SIF) | 110794 | [5 empty] | TRUE | TRUE
142 | Resilience in the Americas (RITA) - El Salvador | IPA- RITA El Salvador | EL SALVADOR | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Field Visits | 400 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 51000 | 400 |  | 107338 | ARC (SIF) | 107338 | [5 empty] | TRUE | TRUE
143 | Resilience in the Americas (RITA) - Panama | IPA- RITA Panama | PANAMA | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Intl Staff Presence | 400 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 37000 | 400 |  | 108164 | ARC (SIF) | 108164 | [5 empty] | TRUE | FALSE
144 | Resilience in the Americas (RITA)- Colombia | IPA -RITA Colombia | COLOMBIA | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | ARC Staff (host country national) | 450 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 2250 | 450 | 2250 | 143582 | ARC (SIF) | 143582 | [5 empty] | TRUE | TRUE
145 | Resilience in the Americas (RITA) - Ecuador | IPA-RITA Ecuador | ECUADOR | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Field Visits | 450 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 2250 | 450 | 2250 | 137856 | ARC (SIF) | 137856 | [5 empty] | TRUE | TRUE
147 | Resilience in the Americas (RITA) - Bahamas | IPA- RITA Bahamas | BAHAMAS | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | American Red Cross - SIF | 2012-06-05 | Implementation | Field Visits | 360 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 15000 | 360 |  | 119350 | ARC (SIF) | 119350 | [5 empty] | TRUE | TRUE
148 | Resilience in the Americas (RITA) - Guyana | IPA- RITA Guyana | GUYANA | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | ARC (SIF) | 2012-06-05 | Implementation | Field Visits | 440 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 2700 | 440 |  | 97450 | ARC (SIF) | 97450 | [5 empty] | TRUE | TRUE
149 | Resilience in the Americas (RITA) - Saint Lucia | IPA- RITA Saint Lucia | SAINT LUCIA | LAC | 2012-06-05 | 2012-10-01 |  |  | Submitted-accepted | ARC (SIF) | 2012-06-05 | Cancelled | NS Only | 400 |  | Integrated | DM - Preparedness/DRR | HNS | [5 empty] | 118450 | ARC (SIF) | 118450 | [5 empty] | TRUE | FALSE | St. Lucia Red Cross was one of the National Socieities that was originally proposed as to conducte the IPA in the Caribbean. After the proposal was accepted, it was decided that St. Lucia Red Cross would not be particpating in the current IPA pilot.
113 | Saving Lives in the Caribbean Through Preparedness | DP - Caribbean Phase III | BAHAMAS | LAC | 2011-09-25 | 2013-11-24 | 2011-08-25 | 2013-08-24 | Submitted-accepted | USAID/OFDA | 2011-04-22 | Implementation | Field Visits | 8507 |  | DM - Preparedness/DRR | Capacity Building | HNS |  | 2011-07-05 | 0 |  |  | 357365 | USAID/OFDA | 357365 | [5 empty] | TRUE | TRUE | No indirect beneficiaries. Struggling with calculating benificiaries..no number as of yet.
151 | Disaster Preparedness for Safer Schools in Bangladesh | DPSS | BANGLADESH | Asia | 2012-08-01 | 2014-01-31 | 2012-08-01 | 2014-01-31 | Submitted-accepted | ARC | 2012-05-10 | Implementation | Field Visits | 20000 |  | DM - Preparedness/DRR |  | HNS |  |  | 60000 |  |  | 467053 | ARC (Restricted Funding) | 467053 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE
153 | Social Mobilization for Measles Campaign 2012 | Soc Mob (India) | INDIA | Asia | 2012-04-01 | 2012-12-31 |  |  | Submitted-accepted | ARC | 2012-04-13 | Closeout | Field Visits | 134000000 |  | Measles |  | Other | [5 empty] | 515341 | ARC (Restricted Funding) | 515341 |  |  |  |  | 100% ARC (SIF & TRP) | FALSE | FALSE | This project is implemented through HNS and IFRC.
7 | Program for Enhancement of Emergency Response | PEER | BANGLADESH | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 1000 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
127 | Enhancement of the Cyclone Preparedness Programme (Phase II) | ECPP II | BANGLADESH | Asia | 2012-05-01 | 2013-04-30 | 2012-05-01 | 2013-04-01 | Submitted-accepted |  | 2012-04-03 | Implementation | Field Visits | 5536 |  | DM - Preparedness/DRR |  | Other |  |  | 7110000 |  |  | 1709224 | ARC (Restricted Funding) | 1709224 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE | This project is implemented through the HNS and IFRC.
157 | Pakistan Measles Campaigns | Pakistan Measles | PAKISTAN | Asia | 2012-07-01 | 2012-12-31 | [5 empty] | Closeout | Field Visits | 10578470 |  | Measles |  | External Partner (non Movement) | [5 empty] | 763000 | ARC | 763000 | [5 empty] | FALSE | FALSE
158 | Resilience in the Americas (RITA) - Belize | IPA- RITA Belize | BELIZE | LAC | 2012-07-01 | 2013-08-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | ARC (SIF) | 2012-06-05 | Implementation | Field Visits | 240 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2012-06-14 | 78000 | 240 |  | 96850 | ARC (SIF) | 96850 | [5 empty] | TRUE | TRUE
159 | Resilience in the Americas (RITA) - Peru | IPA -RITA Peru | PERU | LAC | 2012-12-01 | 2013-08-30 | 2012-12-01 | 2013-06-30 | Submitted-accepted | ARC/SIF | 2013-01-30 | Implementation | Intl Staff Presence | 150 |  | Integrated | DM - Preparedness/DRR | HNS |  | 2013-03-01 | 750 | 150 | 750 | 94225 | ARC (SIF) | 94225 | [5 empty] | TRUE | TRUE | This project has a later start date because the PA was not considered until dropping the project in Paraguay.
160 | Social Mobilization (Namibia) | Soc Mob (Namibia) | NAMIBIA | Africa | 2012-05-01 | 2012-08-31 | 2012-06-29 | 2012-12-30 | Submitted-accepted | ARC - SIF | 2012-06-08 | Closed | Field Visits | 148350 |  | Measles |  | HNS |  | 2012-06-29 |  |  |  | 92741 | ARC (SIF) | 92741 |  |  |  |  | Grant letter funded | FALSE | TRUE
162 | Social Mobilization (Kenya) | Soc Mob (Kenya) | KENYA | Africa | 2012-08-31 | 2012-10-31 | 2012-09-11 | 2013-01-31 | Submitted-accepted | ARCT and ARC SIF | 2012-08-14 | Closed | Intl Staff Presence | 6658778 |  | Measles |  | HNS |  | 2012-09-11 |  |  |  | 380207 | ARCT | 266145 | ARC (SIF) | 114062 |  |  | 70% ARCT, 30% SIF | FALSE | TRUE
163 | Social Mobilization (Cameroon) | Soc Mob (Cameroon) | CAMEROON | Africa | 2012-05-01 | 2012-07-31 | 2012-06-11 | 2012-10-31 | Submitted-accepted | ARC-SIF | 2012-06-11 | Closed | Field Visits | 2012777 |  | Measles |  | HNS | [5 empty] | 29223.9 | ARC (SIF) | 29223.9 |  |  |  |  | PMN | FALSE | TRUE
164 | Social Mobilization (Burundi) | Soc Mob (Burundi) | BURUNDI | Africa | 2012-05-01 | 2012-07-31 | 2012-06-08 | 2012-11-30 | Submitted-accepted |  | 2012-02-23 | Closed | Field Visits | 153354 |  | Measles |  | HNS |  | 2012-06-08 |  |  |  | 154546 | ARC (SIF) | 154546 |  |  |  |  | Grant letter funded | FALSE | FALSE
165 | STAR Organizational Development Project- Peru | STAR Peru | PERU | LAC | 2013-05-06 | [6 empty] | Project Identification & Proposal | Intl Staff Presence |  |  | OD |  | HNS | [13 empty] | TRUE | FALSE
166 | STAR Organizational Development Project-Chile | STAR Chile | CHILE | LAC | 2013-04-08 | [6 empty] | Project Identification & Proposal | Intl Staff Presence |  |  | OD | [15 empty] | TRUE | FALSE
167 | STAR Organizational Development Project-Bahamas | STAR Bahamas | BAHAMAS | LAC | 2013-02-25 | [6 empty] | Project Identification & Proposal | Field Visits |  |  | OD | [15 empty] | FALSE | FALSE
114 | Saving Lives in the Caribbean Through Preparedness | DP - Caribbean Phase III | BELIZE | LAC | 2011-09-25 | 2013-11-24 | 2011-08-25 | 2013-08-24 | Submitted-accepted | USAID/OFDA | 2011-04-22 | Implementation | Field Visits | 55200 |  | DM - Preparedness/DRR |  | HNS |  | 2011-07-05 | 0 |  |  | 345226 | USAID/OFDA | 207136 | ARC (SIF) | 138090 |  |  | 40% ARC and 60% USAID/OFDA | TRUE | TRUE | No indirect beneficiaries. Struggling with calculating benificiaries..no number as of yet.
3 | Regional Health Initiative (Armenia) | HIV - Armenia | ARMENIA | EMECA | 2012-07-01 | 2013-06-30 | 2012-07-01 | 2013-06-30 | Submitted-accepted | ARCT |  | Implementation | Field Visits | 12320 |  | Community Health - HIV |  | HNS |  |  |  | 12320 |  | 550100 | ARCT | 550100 |  |  |  |  | 100% ARCT | TRUE | TRUE
4 | Caribbean HIV/AIDS Project | CHAP I | BAHAMAS | LAC | 2010-08-06 | 2012-08-30 | 2010-07-01 | 2012-06-30 | Submitted-accepted | ARC (SIF) | 2010-08-06 | Closeout | Intl Staff Presence | 9240 |  | Community Health - HIV | [7 empty] | 289395 | ARC (SIF) | 289395 | [5 empty] | TRUE | FALSE | Still some financial reconciliation pending-ISF conducting trips to NS during this quarter
9 | Building Resilient African Communities - CANCELLED | BRACES | BOTSWANA | Africa | 2011-10-01 | 2012-08-31 | [5 empty] | Cancelled | Field Visits | 5524 |  | DM - Preparedness/DRR | [8 empty] | ARCT |  | ARC (SIF) |  |  |  | year 1- 46% ARCT, 54% SIF year 2-70% ARCT, 30% SIF | FALSE | FALSE | PA terminated effective 8/31/12
8 | Regional Health Initiative (Belarus) | HIV - Belarus | BELARUS | EMECA | 2011-02-01 | 2013-06-30 | 2011-07-01 | 2013-06-30 |  |  |  | Implementation | Field Visits | 5320 |  | Community Health - HIV | [7 empty] | 1600000 | ARCT | 1600000 |  |  |  |  | 100% ARCT | TRUE | TRUE
14 | Program for Enhancement of Emergency Response | PEER | CAMBODIA | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
123 | Chile Earthquake Recovery Project | Chile EQ Recovery | CHILE | LAC | 2011-01-11 | 2014-05-31 | 2011-01-11 | 2014-03-31 | Submitted-accepted | ARC | 2011-06-15 | Implementation | Intl Staff Presence | 10000 |  | DM - Recovery | DM - Preparedness/DRR | HNS |  | 2011-06-30 | 50000 | 4000 | 3000 | 1650837 | ARC (Restricted Funding) | 1650837 |  |  |  |  | Restricted Funding- Chile Relief & Development | TRUE | TRUE
16 | HIV Prevention, Care and Support | HIV - China | CHINA | Asia | 2010-05-01 | 2012-12-31 | [5 empty] | Closed | Intl Staff Presence | 127792 |  | Community Health - HIV |  | HNS | [5 empty] | 549364 | ARC (Restricted Funding) | 549364 | [5 empty] | TRUE | FALSE
20 | Regional Humanitarian Action for Refugee and Displaced Populations of the Colombia Conflict and their Host Communities | Refugee/IDP Care - Colombia/Panama | COLOMBIA | LAC | 2011-09-01 | 2012-09-30 |  |  | Submitted-accepted | ARC/SIF | 2011-06-01 | Closed | Intl Staff Presence | 10000 |  | DM - Response | Refugee Care | [6 empty] | 246750 | ARC (SIF) | 246750 | [5 empty] | FALSE | FALSE
110 | Latin America Risk Reduction Activities II | DP - LARRA II | COLOMBIA | LAC | 2011-09-13 | 2013-12-12 | 2011-09-13 | 2013-09-12 | Submitted-accepted | OFDA | 2011-06-30 | Implementation | Intl Staff Presence | 20000 |  | DM - Preparedness/DRR |  | HNS |  | 2011-09-13 | 100000 | 8000 | 10739 | 414832 | ARC (SIF) | 414832 | [5 empty] | TRUE | TRUE | Vulnerable communities throughout Latin America are frequently exposed to natural disasters. Since early 2011, the American Red Cross has been helping community members and Red Cross partners prepare for future disasters through community-based education programs that teach people how to provide basic first aid, and support the installation of early warning systems such as public address (PA) or Very High Frequency (VHF) radio systems. The program is also providing training to Red Cross staff and volunteers on disaster preparedness best practices like keeping a basic emergency kit in the home and actions that individuals should take in the event of an earthquake. Through this regional program, the American Red Cross is working with local Red Cross partners to improve disaster preparedness in Colombia, Costa Rica, Ecuador, El Salvador, Panama and Paraguay. In total, this project aims to reach more than 176,300 people across all six countries.
21 | Latin America Risk Reduction Activities | DP - LARRA | COSTA RICA | LAC | 2010-09-10 | 2012-11-15 | [5 empty] | Closed | Field Visits | 38116 |  | DM - Preparedness/DRR | [7 empty] | 4700000 | ARC (SIF) | 3200000 | Other Private External | 1500000 |  |  | 1,500,000 in funding provided by Merck. | FALSE | FALSE
117 | Latin America Risk Reduction Activities II | DP - LARRA II | COSTA RICA | LAC | 2011-12-01 | 2014-02-28 | 2011-12-01 | 2013-11-30 | Submitted-accepted | SIF | 2011-10-01 | Implementation | Field Visits | 38116 |  | DM - Preparedness/DRR | Water & Sanitation | HNS |  | 2011-10-15 |  |  |  | 421184 | ARCT | 421184 | [5 empty] | TRUE | TRUE | pilot watsan component active
111 | Latin America Risk Reduction Activities II | DP - LARRA II | ECUADOR | LAC | 2011-09-13 | 2013-12-12 | 2011-09-13 | 2013-09-12 | Submitted-accepted | OFDA | 2011-06-30 | Implementation | Field Visits | 12000 |  | DM - Preparedness/DRR |  | HNS |  | 2011-09-13 | 60000 | 6000 | 2388 | 325612 | USAID/OFDA | 325612 | [5 empty] | TRUE | TRUE
33 | Caribbean HIV/AIDS Project | CHAP I | GUYANA | LAC | 2010-08-06 | 2012-08-30 |  |  | Submitted-accepted | ARC (SIF) | 2012-08-06 | Closeout | NS Only | 3690 |  | Community Health - HIV | [7 empty] | 423602 | ARC (SIF) | 423602 | [5 empty] | TRUE | FALSE | Still some financial reconciliation pending-ISF conducting trips to NS during this quarter
35 | [31 empty] | FALSE | FALSE
27 | Latin America Risk Reduction Activities | DP - LARRA | EL SALVADOR | LAC | 2009-09-09 | 2012-09-01 | [5 empty] | Closed | Field Visits | 58785 |  | DM - Preparedness/DRR | [7 empty] | 4700000 | ARC (SIF) | 3200000 | Other Private External | 1500000 |  |  | 1,500,000 funding provided from Merck. | TRUE | FALSE
28 | Improving Community Health in Hurricane Mitch Affected Communities- CDC Water & Sanitation Project | Wat/San Follow Up Model | EL SALVADOR | LAC | 2012-06-01 | 2013-09-30 | 2012-06-01 | 2013-06-30 | Submitted-accepted |  | 2012-04-17 | Implementation | Field Visits | 4345 |  | DM - Recovery | Water & Sanitation | HNS |  | 2012-04-27 |  | 4345 |  | 152824 | ARC (SIF) | 152824 | US Centers for Disease Control | 149850 |  |  | CDC pays contractor's salary; ARC pays project costs. | TRUE | FALSE | Total for all beneficiaries for Guatemala, El Salvador, Honduras and Nicaragua on the proposal is 19,765 (slight discrepancy from adding up country totals). This project has been ongoing (renewed each year) since 1999. Do not have an exact start date.
46 | West Sumatra Organizational Development Project | West Sumatra OD/DM | INDONESIA | Asia | 2010-10-01 | 2013-12-31 | [5 empty] | Implementation | Intl Staff Presence | 11842 |  | OD | DM - Recovery | HNS | [5 empty] | 800875 | ARC (SIF) | 800875 |  |  |  |  | ARC (SIF) funded | TRUE | TRUE
118 | Latin America Risk Reduction Activities II | DP - LARRA II | EL SALVADOR | LAC | 2011-12-01 | 2014-02-28 | 2011-12-01 | 2013-11-30 | Submitted-accepted | SIF | 2011-10-01 | Implementation | Field Visits | 58785 |  | DM - Preparedness/DRR | Water & Sanitation | HNS |  | 2011-10-15 |  |  |  | 373598 | ARC (SIF) | 373598 | [5 empty] | TRUE | TRUE
48 | Strengthening the Indonesian Red Cross Organizational Development Project | Aceh II - OD | INDONESIA | Asia | 2010-11-01 | 2014-06-30 | [5 empty] | Implementation | Intl Staff Presence | 4312 |  | OD |  | HNS | [5 empty] | 499822 | ARC (Restricted Funding) | 499822 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE
30 | Improving Community Health in Hurricane Mitch Affected Communities- CDC Water & Sanitation Project | Wat/San Follow Up Model | GUATEMALA | LAC | 2012-06-01 | 2013-09-30 | 2012-06-01 | 2013-06-30 | Submitted-accepted |  | 2012-04-17 | Implementation | Field Visits | 2565 |  | DM - Recovery | Water & Sanitation | HNS |  | 2012-04-27 |  | 2565 |  | 152824 | ARC (SIF) | 152824 | US Centers for Disease Control | 149850 |  |  | CDC pays contractor's salary; ARC pays project costs. | TRUE | FALSE | Total for all beneficiaries for Guatemala, El Salvador, Honduras and Nicaragua on the proposal is 19,765 (slight discrepancy from adding up country totals). This project has been ongoing (renewed each year) since 1999. Do not have an exact start date.
39 | Improving Community Health in Hurricane Mitch Affected Communities- CDC Water & Sanitation Project | Wat/San Follow Up Model | HONDURAS | LAC | 2012-06-01 | 2013-09-30 | 2012-06-01 | 2013-06-30 |  |  | 2012-04-17 | Implementation | Field Visits | 12385 |  | DM - Recovery | Water & Sanitation | HNS |  | 2012-04-27 |  | 12385 |  | 152824 | ARC (SIF) | 152824 | US Centers for Disease Control | 149850 |  |  | CDC pays contractor's salary; ARC pays project costs | TRUE | FALSE | Total for all beneficiaries for Guatemala, El Salvador, Honduras and Nicaragua on the proposal is 19,765 (slight discrepancy from adding up country totals). This project has been ongoing (renewed each year) since 1999. Do not have an exact start date.
51 | Caribbean HIV/AIDS Project | CHAP I | JAMAICA | LAC | 2010-08-06 | 2012-08-30 |  |  | Submitted-accepted | ARC (SIF) | 2010-08-06 | Closeout | NS Only | 8980 |  | Community Health - HIV |  | HNS | [5 empty] | 422170 | ARC (SIF) | 422170 | [5 empty] | FALSE | FALSE | Still some financial reconciliation pending-ISF conducting trips to NS during this quarter
54 | Regional Health Initiative (Kazakhstan) | HIV - Russia/Central Asia | KAZAKHSTAN | EMECA | 2010-07-01 | 2013-06-30 | [5 empty] | Implementation | Intl Staff Presence | 40000 |  | Community Health - HIV | [7 empty] | 1600000 | ARCT | 1600000 |  |  |  |  | 100% ARCT | TRUE | TRUE | .
57 | Kenya Integrated HIV/AIDS | KY IHIV | KENYA | Africa | 2009-01-01 | 2012-09-30 | 2009-01-23 | 2012-12-31 | Submitted-accepted |  |  | Closed | Intl Staff Presence | 16387 |  | Community Health - HIV |  | HNS |  | 2009-01-23 | 39756 |  |  | 2048975 | ARC (SIF) | 2048975 | [5 empty] | TRUE | TRUE | indirect 39,756
152 | Gujarat Disaster Risk Reduction | Gujarat DRR | INDIA | Asia | 2012-05-01 | 2013-04-30 |  |  | Submitted-accepted |  | 2012-03-03 | Implementation | Field Visits | 1250 |  | DM - Preparedness/DRR |  | HNS |  |  | 2500 |  |  | 59132 | ARC | 59132 | [5 empty] | FALSE | TRUE
43 | Program for Enhancement of Emergency Response | PEER | INDIA | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
154 | Coastal Disaster Risk Reduction | Coastal DRR | INDONESIA | Asia | 2012-10-01 | 2014-09-30 | 2012-10-01 | 2014-09-30 |  |  |  | Implementation | Intl Staff Presence | 90456 |  | DM - Preparedness/DRR |  | HNS |  |  | 1839191 |  |  | 1974942 | ARC (Restricted Funding) | 727033 | USAID/OFDA | 1000000 |  |  | 50% ARC (TRP funded), 50% OFDA funded | TRUE | TRUE
47 | Integrated Community Based Risk Reduction (ICBRR) Project | Aceh II - ICBRR | INDONESIA | Asia | 2010-11-01 | 2014-06-30 | [5 empty] | Implementation | Intl Staff Presence | 26097 |  | DM - Preparedness/DRR |  | HNS | [5 empty] | 705171 | ARC (Restricted Funding) | 705171 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE | Targeted Beneficiaries here are for Phase 2. Phase 1 had it's own targeted beneficiaries.
49 | Aceh Water and Sanitation Project | Aceh II - Wat/San | INDONESIA | Asia | 2010-11-01 | 2014-06-30 | [5 empty] | Implementation | Intl Staff Presence | 20829 |  | DM - Recovery | Water & Sanitation | HNS | [5 empty] | 818901 | ARC (Restricted Funding) | 818901 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE
65139595 | Resilience in the Americas (Peru) | [30 empty] | FALSE | FALSE
65139596 | Regional Humanitarian Action for Refugee and Displaced Populations from the Colombian Conflict and their Host Communities (Phase XI) | PRM Colombia and Ecuador | COLOMBIA | LAC | 2013-09-01 | 2014-08-31 |  |  | Submitted-pending | PRM | 2013-05-15 | Project Identification & Proposal | ARC Staff (host country national) | 35000 |  | Refugee Care | Community Health - General | [6 empty] | 695040 | US State Dept (BPRM) | 586210 | ARC (SIF) | 108830 |  |  |  | TRUE | FALSE
65139597 | Regional Humanitarian Action for Refugee and Displaced Populations from the Colombian Conflict and their Host Communities (Phase XI) | PRM Colombia and Ecuador | ECUADOR | LAC | 2013-09-01 | 2014-08-31 |  |  | Submitted-pending | PRM | 2013-05-15 | Project Identification & Proposal | Field Visits | 35000 |  | Refugee Care | Community Health - General | [6 empty] | 695040 | US State Dept (BPRM) |  | ARC (SIF) |  |  |  |  | FALSE | FALSE
50 | Program for Enhancement of Emergency Response | PEER | INDONESIA | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Intl Staff Presence | 500 |  | DM - Preparedness/DRR |  | HNS | [5 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
82 | Regional Health Initiative (Russia) | HIV - Russia/Central Asia | RUSSIA | EMECA | 2003-01-01 | 2013-06-30 | [5 empty] | Implementation | Intl Staff Presence | 54000 |  | Community Health - HIV |  | HNS | [5 empty] | 1600000 | ARCT | 1600000 |  |  |  |  | 100% ARCT | TRUE | TRUE
90 | Tanzania Integrated HIV/AIDS | TZ IHIV | TANZANIA | Africa | 2009-05-01 | 2013-06-30 |  |  | Under Development |  |  | Implementation | Intl Staff Presence | 2700 |  | Community Health - HIV |  | HNS | [5 empty] | 2467320 | ARC (SIF) | 1837320 | ARCT | 630000 |  |  | SIF through FY12, ARCT starting FY13 | TRUE | FALSE | currently developing proposal for FY14 funding
126 | Greater Jakarta Disaster Risk Reduction | Greater Jakarta | INDONESIA | Asia | 2012-04-01 | 2014-12-31 | [5 empty] | Implementation | Intl Staff Presence | 36549 |  | DM - Preparedness/DRR |  | HNS | [5 empty] | 2257131 | ARC (Restricted Funding) | 2257131 |  |  |  |  | ARC (TRP) funded | TRUE | TRUE
99 | Regional Health Initiative (Ukraine) | HIV - Russia/Central Asia | UKRAINE | EMECA | 2009-07-01 | 2013-06-30 | [5 empty] | Implementation | Intl Staff Presence | 40000 |  | Community Health - HIV |  | HNS | [5 empty] | 232974 | ARCT | 232974 |  |  |  |  | 100% ARCT | TRUE | TRUE
103 | Vietnam Prevention, Care and Support Project | Vietnam HIV/AIDS | VIETNAM | Asia | 2012-07-01 | 2013-06-30 |  |  | Submitted-accepted |  | 2012-03-01 | Implementation | Intl Staff Presence | 12000 |  | Community Health - HIV |  | HNS | [5 empty] | 618655 | ARCT | 618655 |  |  |  |  | 100% ARCT | TRUE | TRUE
128 | Prepare Central Asia: Urban Earthquake Preparedness Initiative | PCA | KAZAKHSTAN | EMECA | 2012-07-01 | 2013-06-30 | [5 empty] | Implementation | Intl Staff Presence | 20000 |  | DM - Preparedness/DRR |  | HNS |  |  |  | 20000 |  | 550100 | ARCT | 550100 |  |  |  |  | Total Budget figure reflective of both Kazakhstan and Turkmenistan. | TRUE | TRUE | Target beneficiaries number reflective of both Kazakhstan and Turkmenistan PCA projects.
106 | STAR Organizational Development Project - Colombia (HR Development) | STAR Colombia | COLOMBIA | LAC | 2012-03-15 | 2013-03-31 | 2012-03-15 | 2012-03-31 | Submitted-accepted | ARCT | 2011-06-05 | Implementation | Field Visits | 300 |  | OD |  | HNS | [5 empty] | 101114 | ARCT | 101114 |  |  |  |  | Grant letter funded (not PA) | FALSE | FALSE | Extended to March 2013
61 | Program for Enhancement of Emergency Response | PEER | LAOS | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
68 | Building Resilient African Communities | BRACES | NAMIBIA | Africa | 2011-10-01 | 2013-09-30 | 2011-10-24 | 2013-12-30 | Submitted-accepted |  | 2011-09-19 | Implementation | Field Visits | 5910 |  | DM - Preparedness/DRR |  | HNS |  | 2011-10-24 |  |  |  | 2326526 | ARCT |  | ARC (SIF) |  |  |  | year 1- 46% ARCT, 54% SIF year 2-70% ARCT, 30% SIF. LOP budget is TOTAL BRACES budget including Namibia, Zimbabwe and Botswana (FY12). | TRUE | TRUE
156 | Developing/Strengthening Community-level Disaster Response Teams | Nepal CADRE | NEPAL | Asia | 2012-06-14 | 2015-06-13 | 2012-06-14 | 2015-06-14 | Submitted-accepted | USAID-OFDA and SIF | 2011-04-23 | Implementation | Field Visits | 576 |  | DM - Preparedness/DRR |  | HNS |  |  | 42240 |  |  | 550000 | USAID/OFDA | 350000 | ARC (SIF) | 200000 |  |  | ~36% ARC (SIF funded) and ~64% OFDA; Agreement End Date above and submission date below are for the Project Agreement between ARC and NRCS (not OFDA award). | TRUE | TRUE | Proposal revised 4/23/2011
69 | Disaster Preparedness for Safer Schools in Nepal - PHASE 2 | DPSS 2 | NEPAL | Asia | 2011-02-01 | 2014-01-31 | [5 empty] | Implementation | Field Visits | 39660 |  | DM - Preparedness/DRR |  |  |  |  | 250000 | 32280 | 10285 | 1297959 | ARCT | 600000 | ARC (SIF) | 441306 |  |  | 66% ARCT; 34% ARC (SIF) | TRUE | TRUE
109 | Program for Enhancement of Emergency Response | PEER | NEPAL | Asia | 2009-04-01 | 2014-03-31 | [5 empty] | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR |  | HNS | [5 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
70 | Improving Community Health in Hurricane Mitch Affected Communities- CDC Water & Sanitation Project | Wat/San Follow Up Model | NICARAGUA | LAC | 2012-06-01 | 2013-09-30 | 2012-06-01 | 2013-06-30 | Submitted-accepted |  | 2012-04-17 | Implementation | Field Visits | 735 |  | DM - Recovery | Water & Sanitation | HNS |  | 2012-04-27 |  | 735 |  | 152824 | ARC (SIF) | 152824 | US Centers for Disease Control | 149850 |  |  | CDC pays contractor's salary; ARC pays project costs | TRUE | TRUE | Total for all beneficiaries for Guatemala, El Salvador, Honduras and Nicaragua on the proposal is 19,765 (slight discrepancy from adding up country totals). This project has been ongoing (renewed each year) since 1999. Do not have an exact start date.
122 | Program for Enhancement of Emergency Response | PEER | PAKISTAN | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | FALSE
76 | Regional Humanitarian Action for Refugee and Displaced Populations of the Colombia Conflict and their Host Communities | Refugee/IDP Care - Colombia/Panama | PANAMA | LAC | 2011-09-01 | 2012-11-30 | [5 empty] | Closed | Intl Staff Presence | 10000 |  | DM - Response | Refugee Care | [6 empty] | 532146 | US State Dept (BPRM) | 450000 | ARC (SIF) | 82146 |  |  |  | TRUE | FALSE
119 | Latin America Risk Reduction Activities II | DP - LARRA II | PANAMA | LAC | 2011-12-01 | 2014-02-28 | 2011-12-01 | 2013-11-30 | Submitted-accepted | SIF | 2011-10-01 | Implementation | Field Visits | 41448 |  | DM - Preparedness/DRR | Water & Sanitation |  |  | 2011-10-15 |  |  |  | 330108 | ARC (SIF) | 330108 | [5 empty] | TRUE | TRUE
112 | Latin America Risk Reduction Activities II | DP - LARRA II | PARAGUAY | LAC | 2011-09-13 | 2013-12-12 | 2011-09-13 | 2013-09-12 | Submitted-accepted | OFDA | 2011-06-30 | Closeout | Field Visits | 6000 |  | DM - Preparedness/DRR |  | HNS |  | 2011-09-13 | 30000 | 3000 | 296 | 345660 | USAID/OFDA | 345660 | [5 empty] | TRUE | TRUE | Activites have been suspended as of November 2012 due to financial irregularities. ARC is closing out project.
78 | Latin America Risk Reduction Activities | DP - LARRA | PERU | LAC | 2012-07-01 | 2013-10-31 | 2012-07-01 | 2013-08-31 | Submitted-accepted | Merck | 2009-06-01 | Implementation | Intl Staff Presence | 300 |  | DM - Preparedness/DRR | Capacity Building |  |  | 2009-08-01 |  | 200 |  | 70000 | ARC (Other) | 70000 | [5 empty] | TRUE | TRUE | Focus on NS capacity building
120 | Program for Enhancement of Emergency Response | PEER | PHILIPPINES | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Field Visits | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
116 | Saving Lives in the Caribbean Through Preparedness | DP - Caribbean Phase III | SAINT LUCIA | LAC | 2011-09-25 | 2013-11-24 | 2011-08-25 | 2013-08-24 | Submitted-accepted | USAID/OFDA | 2011-04-22 | Implementation | Field Visits | 11553 |  | DM - Preparedness/DRR |  | HNS |  | 2011-07-02 | 0 |  |  | 329790 | USAID/OFDA | 329790 | [5 empty] | TRUE | TRUE | No indirect beneficiaries. Struggling with calculating benificiaries..no number as of yet.
115 | ICRC Annual Appeal for Darfur | ICRC Darfur | SUDAN | Africa | [7 empty] | Implementation | None |  |  | DM - Response | [15 empty] | FALSE | FALSE
91 | Emergency Assistance to Congolese & Burundian Refugees in Tanzania | TZ BPRM | TANZANIA | Africa | 2004-09-01 | 2013-08-31 | 2012-09-01 | 2013-08-31 | Submitted-accepted | BPRM | 2012-08-13 | Implementation | Intl Staff Presence | 122230 |  | DM - Response | Refugee Care | HNS |  | 2012-11-15 |  |  |  | 520479 | US State Dept (BPRM) | 520479 |  |  |  |  | This is budget for year 9. See PO for information about previous years. | TRUE | TRUE
129 | Prepare Central Asia: Urban Earthquake Preparedness Initiative | PCA | TURKMENISTAN | EMECA | 2012-07-01 | 2013-06-30 | [5 empty] | Implementation | Field Visits | 20000 |  | DM - Preparedness/DRR | [5 empty] | 20000 |  | 550100 | ARCT | 550100 |  |  |  |  | Total Budget figure is reflective of both Turkmenistan and Kazakhstan. | TRUE | TRUE | Target beneficiaries number reflective of both Kazakhstan and Turkmenistan PCA projects.
124 | Prepare Uganda: Reducing Risks in Urban Communities | Urban DP | UGANDA | Africa | 2012-07-01 | 2014-12-31 | 2012-07-06 | 2015-03-30 | Submitted-accepted |  | 2012-06-08 | Implementation | Intl Staff Presence | 30000 |  | DM - Preparedness/DRR |  | HNS |  | 2012-07-06 | 55000 |  |  | 1064249 | ARCT | 280000 | ARC (SIF) | 120000 |  |  | Funding source amounts are for Year 1 only. Funding sources for Year 2 are TBD. | TRUE | TRUE
125 | Manafwa River Basin | Manafwa | UGANDA | Africa | 2012-07-01 | 2015-06-30 | 2012-07-06 | 2015-09-30 | Submitted-accepted |  | 2012-06-14 | Implementation | Intl Staff Presence | 75000 |  | DM - Preparedness/DRR |  | HNS |  | 2012-07-06 |  |  |  | 1793353 | ARCT | 325449 | USAID/OFDA | 498919 |  |  | OFDA funding source amount is for Yr 1 and 2. ARCT is for Yr 1. Rest is TBD/SIF for yr 2 and 3; ARCT funding is only secured for the first year, but expected for years 2 and 3 | TRUE | TRUE
168 | Vietnam Forests and Deltas | Vietnam Winrock | VIETNAM | Asia | 2012-10-22 | 2013-10-17 |  |  | Submitted-accepted | USAID | 2012-06-01 | Planning | Intl Staff Presence |  |  | DM - Preparedness/DRR | [7 empty] | 5886681 | USAID/OFDA | 4886681 | ARC (SIF) | 1000000 |  |  |  | TRUE | FALSE | LOP Budget is ARC's portion only. We are a sub to Winrock as the prime; Chau not sure of benef numbers; will do some more research.
104 | Disaster Risk Reduction Expanded Program in Vietnam | Vietnam DRR | VIETNAM | Asia | 2010-10-01 | 2013-09-30 | [5 empty] | Implementation | Intl Staff Presence | 140000 |  | DM - Preparedness/DRR | [7 empty] | 1122601 | USAID/OFDA | 491266 | ARCT | 400000 | ARC (SIF) | 376889 |  | TRUE | TRUE
121 | Program for Enhancement of Emergency Response | PEER | VIETNAM | Asia | 2009-04-01 | 2014-03-31 |  |  | Submitted-accepted |  | 2008-08-28 | Implementation | Intl Staff Presence | 500 |  | DM - Preparedness/DRR | [7 empty] | 1068260 | ARC | 1068260 |  |  |  |  | Total LOP budget is reflective of total combined figures for all nine PEER countries. | TRUE | TRUE
107 | Building Resilient African Communities | BRACES | ZIMBABWE | Africa | 2011-10-01 | 2013-09-30 | 2011-11-04 | 2013-12-31 | Submitted-accepted |  | 2011-09-19 | Implementation | Field Visits | 9875 |  | DM - Preparedness/DRR |  | HNS |  | 2011-11-04 |  |  |  | 2326526 | ARCT |  | ARC (SIF) |  |  |  | year 1- 46% ARCT, 54% SIF; year 2-70% ARCT, 30% SIF. LOP budget is TOTAL BRACES budget including Namibia, Zimbabwe and Botswana (FY12). | TRUE | TRUE
130 | Caribbean HIV/AIDS Project | CHAP II | BAHAMAS | LAC | 2012-07-01 | 2014-08-30 | 2012-07-01 | 2014-06-30 | Submitted-accepted | ARC (SIF) | 2012-05-01 | Implementation | Field Visits |  |  | Community Health - HIV |  | HNS |  | 2012-05-11 |  | 8807 | 2909 | 566526 | ARC (SIF) | 566526 | [5 empty] | TRUE | TRUE | CHAP II only has target benificiaries for FY13. FY14 has not been determined yet hence the lack of data for LOP target beneficiaries
131 | Caribbean HIV/AIDS Project | CHAP II | GUYANA | LAC | 2012-07-01 | 2014-08-30 | 2012-07-01 | 2014-06-30 | Submitted-accepted | ARC (SIF) | 2012-05-01 | Implementation | Field Visits |  |  | Community Health - HIV |  | HNS |  | 2012-05-11 |  | 2773 | 747 | 492457 | ARC (SIF) | 492457 | [5 empty] | TRUE | TRUE | CHAP II only has target benificiaries for FY13. FY14 has not been determined yet hence the lack of data for LOP target beneficiaries
132 | Caribbean HIV/AIDS Project | CHAP II | JAMAICA | LAC | 2012-07-01 | 2014-08-30 | 2012-07-01 | 2014-06-30 | Submitted-accepted | ARC (SIF) | 2012-05-01 | Implementation | Field Visits |  |  | Community Health - HIV |  | HNS |  | 2012-05-11 |  | 4725 | 1578 | 437642 | ARC (SIF) | 437642 | [5 empty] | TRUE | TRUE | CHAP II only has target benificiaries for FY13. FY14 has not been determined yet hence the lack of data for LOP target beneficiaries
133 | Integrated Health-DRR | Wonogiri DRR/CBHFA | INDONESIA | Asia | 2012-03-25 | 2014-12-24 | [5 empty] | Implementation | Intl Staff Presence | 116838 |  | Integrated |  | HNS | [5 empty] | 323410 | ARC | 173410 | OTHER | 15000 |  |  | 50% ARC and 50% Spanish Red Cross | TRUE | TRUE
134 | PMER System Development | OD PMER | INDONESIA | Asia | 2013-01-01 | 2015-12-31 |  |  | Submitted-accepted | Internal | 2013-02-12 | Project Identification & Proposal | Intl Staff Presence | 1600 |  | OD |  |  |  | 2013-02-21 |  |  |  | 600000 | ARC (Restricted Funding) | 600000 |  |  |  |  | ARC (TRP) funded | FALSE | FALSE
135 | STAR Organizational Development Project - Namibia (Internal Communication) | STAR Namibia | NAMIBIA | Africa | 2012-08-01 | 2013-05-31 |  |  | Submitted-accepted | ARCT | 2012-11-16 | Implementation | Field Visits |  |  | OD |  | Other | [5 empty] | 26615 | ARCT | 26615 |  |  |  |  | Grant letter funded | FALSE | FALSE | Implemented directly and through the HNS. The initial project was scheduled to end 1/31/13, but it has been extended to 5/31/13 to include a comms audit.
136 | STAR Organizational Development Project - South Africa | STAR South Africa | SOUTH AFRICA | Africa | [7 empty] | Cancelled |  |  |  | OD | [14 empty] | PA is not in place; will potentially start initial activities at end of FY13 but not sure | FALSE | FALSE
137 | STAR Organizational Development Project- Uganda (Org Learning) | STAR Uganda | UGANDA | Africa | 2013-04-01 | 2013-07-19 |  |  | Submitted-pending | Internal | 2013-04-03 | Project Identification & Proposal | Intl Staff Presence |  |  | OD |  | HNS | [5 empty] | 5239 | ARCT | 5239 |  |  |  |  | Project proposal is in the process of being approved. | FALSE | FALSE
138 | STAR Organizational Development Project- El Salvador (Financial Mgmt) | STAR El Salvador | EL SALVADOR | LAC | 2013-03-18 | 2014-05-19 | 2013-03-18 | 2014-03-19 | Submitted-accepted | ARCT |  | Implementation | Field Visits |  |  | OD | [7 empty] | 93504 | ARCT | [5 empty] | grant letter funded | FALSE | FALSE | grant funded; grant letter under review with NS
139 | STAR Organizational Development Project- Nepal | STAR Nepal | NEPAL | Asia | [7 empty] | Project Identification & Proposal | Field Visits |  |  | OD | [14 empty] | PA is not in place; will potentially start initial activities at end of FY13 but not sure | FALSE | FALSE
169 | Disaster Preparedness and Response Training for Red Cross Society of China, Phase II | China DM Training | CHINA | Asia | 2013-03-01 | 2014-06-20 |  |  | Submitted-accepted | Internal | 2013-02-06 | Project Identification & Proposal | Intl Staff Presence | 225 |  | DM - Preparedness/DRR | Capacity Building |  |  | 2013-03-08 |  |  |  | 134674 | ARC (Restricted Funding) | [6 empty] | TRUE | TRUE
170 | Social Mobilization (Ethiopia) | Soc Mob (Ethiopia) | ETHIOPIA | Africa | 2013-05-27 | 2013-06-07 |  |  | Submitted-accepted | Internal | 2013-04-02 | Project Identification & Proposal | Field Visits | 120647 |  | Measles |  | HNS |  | 2013-04-07 |  | 120647 |  | 161054 | ARCT | 161054 | [5 empty] | FALSE | TRUE
171 | Social Mobilization (Rwanda) | Soc Mob (Rwanda) | RWANDA | Africa | 2013-02-01 | 2013-04-01 | 2013-02-06 | 2013-07-01 | Submitted-accepted |  | 2013-01-28 | Closeout | Field Visits | 748487 |  | Measles |  | HNS |  | 2013-02-06 |  | 748487 |  | 109706 | ARCT | 109706 | [5 empty] | FALSE | TRUE
172 | Corporate Volunteers | Corporate Volunteers | INDONESIA | Asia | 2013-01-01 | 2014-12-31 |  |  | Submitted-pending | Internal | 2013-01-24 | Project Identification & Proposal | Intl Staff Presence | 614 |  | OD |  | HNS |  |  | 6402 |  |  | 400000 | ARC (Restricted Funding) | 400000 |  |  |  |  | 100% ARC (TRP) funded | TRUE | FALSE
173 | Social Mobilization for Measles-Rubella Campaign 2012 | Soc Mob (Nepal) | NEPAL | Asia | 2012-03-01 | 2012-10-31 | 2012-03-01 | 2013-03-31 | Submitted-accepted |  |  | Implementation | Field Visits | 1172622 |  | Measles |  | HNS | [5 empty] | 112421 | ARC | 112421 | [5 empty] | FALSE | TRUE
65139588 | FY14 Resilience in the Americas (RITA)- Bahamas | RITA-Bahamas | BAHAMAS | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139589 | FY14 Resilience in the Americas (RITA)-Guyana | RITA-Guyana | GUYANA | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139590 | FY14 Resilience in the Americas (RITA)-Belize | RITA-Belize | BELIZE | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139591 | FY14 Resilience in the Americas (RITA)- Nicaragua | RITA-Nicaragua | NICARAGUA | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139592 | FY14 Resilience in the Americas (RITA)-Costa Rica | RITA-Costa Rica | COSTA RICA | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139593 | FY14 Resilience in the Americas (RITA)-El Salvador | RITA-El Salvador | EL SALVADOR | LAC | 2013-07-01 | 2013-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139594 | FY14 Resilience in the Americas (RITA)-Panama | RITA-Panama | PANAMA | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Intl Staff Presence |  |  | Integrated |  | HNS | [13 empty] | TRUE | FALSE
65139585 | FY14 Resilience in the Americas (RITA)- Colombia | RITA - Colombia | COLOMBIA | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated | DM - Preparedness/DRR | HNS | [13 empty] | TRUE | FALSE
65139586 | FY14 Resilience in the Americas (RITA)- Ecuador | RITA - Ecuador | ECUADOR | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Field Visits |  |  | Integrated | DM - Preparedness/DRR | HNS | [13 empty] | TRUE | FALSE
65139587 | FY14 Resilience in the Americas (RITA)- Peru | RITA - Peru | PERU | LAC | 2013-07-01 | 2014-06-30 |  |  | Submitted-pending | ARCT | 2013-02-27 | Project Identification & Proposal | Intl Staff Presence |  |  | Integrated | DM - Preparedness/DRR | HNS | [13 empty] | TRUE | FALSE
256 | [31 empty] | FALSE | FALSE
| Count | 38